## Task Tracker
TEAM TASK & PRODUCTIVITY TRACKER
Track assignments, deadlines, and workload across all team members and brands
Task ID | Task Name | Assigned To | Brand | Task Type | Priority | Status | Start Date | Deadline | Completion Date | Notes
TSK-001 | Instagram Reels - Product Launch | Dimas Prasetyo | Tunova | Social Media Post | Medium | In Progress | 2026-04-05 | 2026-04-11
TSK-002 | Facebook Ad Campaign Q2 | Dimas Prasetyo | Tunova | Video Production | Medium | Not Started | 2026-04-03 | 2026-04-12
TSK-003 | Brand Guidelines Update | Dewi Lestari | Tunova | Brand Guidelines | High | In Progress | 2026-04-21 | 2026-05-11
TSK-004 | Monthly Newsletter Draft | Fajar Nugroho | Tunova | Email Marketing | Medium | Completed | 2026-04-01 | 2026-04-09 | 2026-04-06
TSK-005 | TikTok Content Calendar | Putri Wulandari | Tunova | Graphic Design | High | Completed | 2026-04-04 | 2026-04-09 | 2026-04-06
TSK-006 | Product Photography Session | Siti Rahayu | Tunova | Ad Management | Medium | Completed | 2026-04-24 | 2026-05-11 | 2026-05-11
TSK-007 | Website Banner Design | Fajar Nugroho | Tunova | Photography | High | In Review | 2026-04-12 | 2026-05-03
TSK-008 | Email Drip Campaign Setup | Dewi Lestari | Tunova | Social Media Post | Medium | Completed | 2026-04-03 | 2026-04-13 | 2026-04-13
TSK-009 | Influencer Outreach List | Fajar Nugroho | Tunova | Email Marketing | Medium | In Progress | 2026-04-12 | 2026-04-26
TSK-010 | YouTube Video Editing | Dewi Lestari | Tunova | Event Planning | Low | In Review | 2026-04-20 | 2026-04-28
TSK-011 | Blog Post - Industry Trends | Hendra Wijaya | Tunova | Graphic Design | Medium | In Progress | 2026-04-21 | 2026-05-11
TSK-012 | Press Release Draft | Dewi Lestari | Tunova | Social Media Post | High | Not Started | 2026-04-11 | 2026-04-26
TSK-013 | Social Media Audit Report | Rizki Hidayat | Tunova | Copywriting | Low | In Review | 2026-04-23 | 2026-05-06
TSK-014 | Google Ads Optimization | Dewi Lestari | Tunova | Content Strategy | Low | In Review | 2026-04-05 | 2026-04-16
TSK-015 | Landing Page Wireframe | Budi Santoso | Tunova | Event Planning | Medium | In Progress | 2026-04-19 | 2026-05-05
TSK-016 | Customer Testimonial Video | Maya Kusuma | Natasha | Ad Management | High | On Hold | 2026-04-17 | 2026-05-05
TSK-017 | Podcast Episode Editing | Siti Rahayu | Natasha | Video Production | High | Not Started | 2026-04-22 | 2026-05-08
TSK-018 | Competitor Analysis Report | Maya Kusuma | Natasha | Content Strategy | Medium | On Hold | 2026-04-17 | 2026-04-28
TSK-019 | Whitepapers Design Layout | Hendra Wijaya | Natasha | Market Research | Medium | Completed | 2026-04-18 | 2026-04-29 | 2026-04-27
TSK-020 | Trade Show Materials | Siti Rahayu | Natasha | Content Strategy | High | Not Started | 2026-04-24 | 2026-05-05
TSK-021 | Holiday Campaign Planning | Hendra Wijaya | Natasha | Photography | Low | Completed | 2026-04-10 | 2026-04-29 | 2026-04-28
TSK-022 | SEO Content Brief | Budi Santoso | Natasha | Graphic Design | Medium | Completed | 2026-04-17 | 2026-04-20 | 2026-04-18
TSK-023 | Brand Awareness Survey | Anita Sari | Natasha | Video Production | Low | Completed | 2026-04-26 | 2026-05-08 | 2026-05-07
TSK-024 | Partnership Proposal Deck | Adi Pratama | Natasha | Brand Guidelines | Low | Not Started | 2026-04-16 | 2026-04-21
TSK-025 | Weekly Analytics Report | Hendra Wijaya | Natasha | Graphic Design | Medium | On Hold | 2026-04-06 | 2026-04-17
TSK-026 | Creative Brief - New Product | Hendra Wijaya | Natasha | Content Strategy | Low | On Hold | 2026-04-25 | 2026-05-04
TSK-027 | Radio Ad Script | Rina Fitriani | Natasha | Content Strategy | Low | In Review | 2026-04-15 | 2026-05-04
TSK-028 | Billboard Design Concept | Anita Sari | Natasha | Copywriting | High | In Progress | 2026-04-19 | 2026-05-09
TSK-029 | App Store Screenshots | Dewi Lestari | Natasha | Copywriting | High | Completed | 2026-04-02 | 2026-04-12 | 2026-04-12
TSK-030 | Loyalty Program Email | Adi Pratama | NaavaGreen | Video Production | Medium | In Progress | 2026-04-16 | 2026-04-25
TSK-031 | Webinar Presentation Slides | Hendra Wijaya | NaavaGreen | Event Planning | Low | In Review | 2026-04-16 | 2026-04-26
TSK-032 | Annual Report Design | Anita Sari | NaavaGreen | Copywriting | High | In Review | 2026-04-12 | 2026-04-28
TSK-033 | Social Listening Report | Fajar Nugroho | NaavaGreen | Event Planning | High | In Review | 2026-04-21 | 2026-04-27
TSK-034 | Rebranding Mood Board | Adi Pratama | NaavaGreen | Event Planning | Medium | Completed | 2026-04-08 | 2026-04-17 | 2026-04-16
TSK-035 | Video Testimonials Edit | Hendra Wijaya | NaavaGreen | Graphic Design | Medium | In Progress | 2026-04-08 | 2026-04-13
TSK-036 | Content Repurposing Plan | Anita Sari | NaavaGreen | Video Production | High | On Hold | 2026-04-01 | 2026-04-06
TSK-037 | Content Repurposing Plan | Anita Sari | NaavaGreen | Video Production | High | On Hold | 2026-04-01 | 2026-04-06
TSK-038 | Content Repurposing Plan | Anita Sari | NaavaGreen | Video Production | High | On Hold | 2026-04-01 | 2026-04-06
TSK-039 | Content Repurposing Plan | Anita Sari | NaavaGreen | Video Production | High | On Hold | 2026-04-01 | 2026-04-06
TSK-040 | Content Repurposing Plan | Anita Sari | NaavaGreen | Video Production | High | On Hold | 2026-04-01 | 2026-04-06
TSK-041 | Content Repurposing Plan | Anita Sari | NaavaGreen | Video Production | High | On Hold | 2026-04-01 | 2026-04-06

## Team Members
TEAM DIRECTORY
Name | Role | Department | Max Capacity (tasks/week)
Adi Pratama | Content Creator | Content | 5
Siti Rahayu | Graphic Designer | Design | 5
Budi Santoso | Social Media Manager | Social Media | 7
Dewi Lestari | Copywriter | Content | 7
Rizki Hidayat | Video Editor | Production | 7
Putri Wulandari | Campaign Manager | Marketing | 5
Fajar Nugroho | Content Strategist | Strategy | 7
Anita Sari | Email Specialist | Marketing | 4
Hendra Wijaya | Photographer | Production | 5
Maya Kusuma | Brand Manager | Brand | 7
Dimas Prasetyo | Market Analyst | Research | 4
Rina Fitriani | Event Coordinator | Events | 7

## Brands
BRAND DIRECTORY
Brand Name | Industry | Status
Tunova | Technology | Active
Bank Mantap | Finance | Active
Barklay | Pet | Active
Natasha | Beauty & Skincare | Active
NaavaGreen | Beauty & Skincare | Active

## Summary
TASK SUMMARY
Total Tasks | 41
Completed | 10
In Progress | 8
Overdue (past deadline, not completed) | 20
TASKS PER TEAM MEMBER
Team Member | Total | Not Started | In Progress | In Review | Completed
Adi Pratama | 3 | 1 | 1 | 0 | 1
Siti Rahayu | 3 | 2 | 0 | 0 | 1
Budi Santoso | 2 | 0 | 1 | 0 | 1
Dewi Lestari | 6 | 1 | 1 | 2 | 2
Rizki Hidayat | 1 | 0 | 0 | 1 | 0
Putri Wulandari | 1 | 0 | 0 | 0 | 1
Fajar Nugroho | 4 | 0 | 1 | 2 | 1
Anita Sari | 9 | 0 | 1 | 1 | 1
Hendra Wijaya | 7 | 0 | 2 | 1 | 2
Maya Kusuma | 2 | 0 | 0 | 0 | 0
Dimas Prasetyo | 2 | 1 | 1 | 0 | 0
Rina Fitriani | 1 | 0 | 0 | 1 | 0
TASKS PER BRAND
Brand | Total | Not Started | In Progress | In Review | Completed
Brand Alpha | 0 | 0 | 0 | 0 | 0
Brand Beta | 0 | 0 | 0 | 0 | 0
Brand Gamma | 0 | 0 | 0 | 0 | 0
Brand Delta | 0 | 0 | 0 | 0 | 0
Brand Epsilon | 0 | 0 | 0 | 0 | 0